## Slide 1: Pilot retrospective
Customer portal pilot, January to June 2026

## Slide 2: Agenda
What we set out to do
Lessons learned
Next steps

## Slide 3: Lessons learned
Planning
  The scope was agreed two weeks after the pilot started
  Estimates for data migration were 40% too low
  Weekly planning sessions worked well once they started
Delivery
  Releasing every two weeks kept stakeholders engaged
  Manual testing slowed down the last three releases
  The rollback plan was never tested
People
  Two key developers left in month four
  Pairing new joiners with experienced staff shortened onboarding
  Business testers were only available on Fridays
Tooling
  The shared test environment was often down
  Moving the backlog to one board removed duplicate work
  Monitoring dashboards arrived too late to help
Customers
  Pilot customers liked the self-service invoices most
  Support calls fell by 18% in the pilot group
  Customers asked for a mobile app in almost every interview
Notes: Planning: the late scope agreement is the root cause of most of the slippage.
Delivery: the fortnightly releases are the thing to keep; the untested rollback is the thing to fix first.
People: the two departures cost us about six weeks.
Tooling: we will ask for a dedicated test environment in the next phase.
Customers: the 18% fall in support calls is the strongest evidence for a full rollout.

## Slide 4: Next steps
Agree the scope for the full rollout by 15 November
Automate the regression tests
Book business testers for two days a week